## Q1
Updated:Feb 13 - GW
Work Break Down Structure - Q1-Q2 HPS Administrative Implementation Pieces
Week of
|  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May
Deliverable/Recommendation |  | Sub-Deliverable(s) | POINT PERSON(S) |  | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | …
1. Aligning internal administrative job functions and practices
a) The HSD should consider aligning the job portfolios of Contract Analysts by service delivery agent; not by funding stream.
| 1.1 | Identify Service Delivery Agents and Programs that align for 2014
| 1.2 | Facilitate discussion between Contracts Analyst re: alignment of specific portfolios
| 1.3 | Establish criteria to be used for Program Manager to make decisions regarding portfolio management
| 1.4 | Develop a communications to agencies re: changes
| 1.5 | Communicate changes to agencies
| c) The HSD should establish with the Finance Department a coordinated approach for the exchange of financial forecasting information. This free exchange of information about cash flow projections can be facilitated through the development of a coordinated and relational database in an updated Information Management System | Review current template and suggest changes under the new funding processes
2.Alignment of Person -Centered administrative practices with the HSD's principle of person centered programming
a) The HSD should continue to work towards a person-centered approach to administrating and monitoring HPS projects. The HSD should (as much as possible) offer a ‘one-window approach’ in administering programs, meaning a single point of contact should be established for all homelessness programming offered through a 3rd party agency, regardless of funding source.
| 2.1 | Identify single point of contact for each agency, in areas where a project might require additional City Contacts - identify who and for what purposes
| 2.2 | Inform agency's who their single contact will be. In the event of multiple contacts, in writing explain who the contact will be and for what specific purpose.
| 2.3 | Flow diagrams may need to be developed for internal processes for each type of request to assist in standardizing/aligning processes. (Cash Flow requests - 'Single Point of Contact' - HSD person #1 - City person #2 - etc)
| 2.4 | Develop a communications to agencies re: any changes
| 2.5 | Communicate changes to agencies
4. Creating Monitoring Plans
a) Monitoring activities should be scheduled as part of a plan developed by the Contracts Analyst with consultation and advice of the Program Manager at the beginning of a project’s contract. The monitoring plan and monitoring schedule should be informed by the community planning timelines of the individual agency. <See Recommendation #2>
| Development of the Template - 4.1 | Discussion with Team re: Principles, purposes and critical components of monitoring plans + key dates and themes | Amanda
| 4.2 | Identification of any 'other' components that might be useful to be included in plans
| 4.3 | Development of template of monitoring plans (draft)
| 4.4 | Review of template of moniotring plans
| 4.5 | Improvement of monitoring plan document, development of Final Draft of monitoring plan template
| Contract alignment - 4.6 | Discussion between Contracts Analysts and Management on how to embed plans in the Contracts or not at all (separate schedule OR apart from the contracts or embed within an existing schedule, etc)
| 4.7 | Development of language in the contract to include monitoring plans
| Development of process for Monitoring Plan - 4.8 | Development of process for the completion of monitoring plans for each agency
| Creation of individualized Monitoring Plans by Project - 4.9 | Creation of individualized Monitoring Plans by Project
| Liase with Agencies - 4.10 | Communication with agencies re: appraoch on monitoring schedules/submission schedules
| 4.11 | Dissemination of Monitoring Plans to agencies
6. There should be a renewed focus on monitoring program data & information related to project outcomes, not project activities.
There should be a renewed focus on monitoring program data & information related to project outcomes, not project activities.
| 6.1 | Identify all project outcome indicators, Identify project outcomes indicators relevant as they relate to specific HPS projects in 2014-2015
| 6.2 | Summarize the Outcomes that will be targeted, monitored and tracked
| 6.3 | Identify project financial outcomes that will be targeted, measured and tracked
| 6.4 | Develop process for identifying and addressing project risks when targets are not being achieved
| 6.5 | Develop tools (if needed, see recommendation #7) to track and monitor project outcomes
| 6.6 | Integrate project-specific outcome measures into monitoring plans
| 6.7 | Develop monitoring process/any tools to support ongoing disucssions with agencies (or to assist in liaising with stakeholders: HH Planning Grp, CAB etc) regarding project performance outcomes as well as financial outcomes
7. The responsibility of financial outcome tracking should fall to the Contracts Analyst and staff
The responsibility of financial outcome tracking should fall to the Contracts Analyst and staff
| 7.1 | Determine which staff will be involved in future financial outcome tracking - for each project
| 7.2 | Communicate new responsibilities re: portfolio to staff
| 7.3 | Integrate the work of the creation of new outcome monitoring tools into the skill-set of staff. As much as possible autmated tracking tools should be used.
| 7.4 | Identify training opportunities for staff re: using financial outcome tracking tools - coordinate process
| 7.5 | Standardize and coordinate the process in which financial outcome monitoring will follow - monthly/quarterly etc. Who inputs data into tools (see Rec #8), who analyses data, how often, who communicates it etc.
8. Develop new outcome monitoring tools & consolidate current monitoring tools
a) Modelling tools, tracking tools and visualizations should be developed to regularly track financial outcomes. These tools would be mainly to measure whether project spending is on track to meet quarterly/annual targets. They may provide additional uses as policy and planning tools.
| 8.1 | Determine key financial components that need to be tracked and measured
| 8.2 | Identify the process which will optimize transfering the information gathered via project financial monitoring into a model/tool that will ultimately assess the progress of a project - based on that process should be the creation of outcome monitoring tools. The tools should not be created and the process fit around them
| 8.3 | Determine audience(s) for financial outcome monitoring progress
| 8.4 | Determine potential ways to visualize financial data, there may be different ways needed to illustrate outcomes based on audiences
| 8.5 | Development of Financial Outcome Tracking tool(s) (drafts)
| 8.6 | Pilot of tools, feedback gathered and changes made to tools
| 8.7 | Development of Final versions of financial outcome tracking tools
| 8.8 | Integrate communication of financial outcomes (using tools) to audiences into monitoring plans
9. Convert to a payment’s system using advanced quarterly payments
a) Using the reporting forms borrowed from the City of Ottawa, the HSD should develop a similar set of reporting/monitoring forms to facilitate this conversion.
| 9.1 | Identify who will be involved in reforming the payments process | Amanda | bar: 20
| 9.2 | Distribute the forms borrowed from the City of Ottawa to the persons who will be involved in reforming the payments process - to familiarize all with what will be the ultimate goal | Greg | bar: 20
| 9.3 | Review City of Ottawa forms - determine what information re: process and the templates themselves we can glean to assist in the development of an advanced payments process | All | bar: 27
| 9.4 | Liaise with Legal re: what changes would have to be included within the contracts w 3rd party agencies (HPS) seeing that we are switching to an advanced payments system; integrate those changes into the contract design; initiate contract signing process | Lorne & Jolanta | bar: 27 to March 17
| 9.5 | Finance to provide input on challenges and consideration in transitioning to advanced payments | Jenny Gibson & Merlene | bar: February 17
| 9.6 | Present CHPI payments and Reconciliation Process to the Project Team at Interventions meeting | Lorne | bar: February 3
| 9.7 | Develop a draft Payments and Reconciliation Process - bring forward recommendation for the process to the Inverventions Meeting including identifying a list of all forms/templates that will need to be created …. Considerations include: What is the payments schedule??? - financial submissions from agencies (date and content needed to submit), payment trigger, payment dates, reconcoliation of payments schedule, communications to agencies | Greg | bar: February 10
| 9.8 | Decide/Approve Payments/Reconciliation Schedule | Amanda | bar: February 17
| 9.9 | Liase with HPS admin: consult re: requirements around quantity/quality of backup documentation to be provided as part of payments process | Amanda | bar: February 17
| 9.1 | Draft templates for made in Hamilton versions of any forms/templates that will need to be created or modified for facilitating the advanced payments process | John | bar: February 24 to March 3
| 9.11 | Take the draft/point form payments process/schedule developed previously along with notes from finance/HPS and finalize P&P | Greg | bar: February 24 to March 3
| 9.12 | Decision/Approval of Procedure | Amanda | bar: March 10
| 9.13 | Decision/Approval of Any new forms/templates | Amanda | bar: March 10
| 9.14 | Draft a communication to agencies re: change in process | Greg | bar: March 10
| 9.15 | Review and send communication to agencies re: change in process | Amanda | bar: March 17
| 9.16 | Liase with HPS agencies re: change in process from 2014-2019 (payments) | Jolanta & Lorne | bar: 27 to March 31
10. Establish hard reporting deadlines for the submission of financial (and activity) monitoring information from 3rd party agencies.
Establish hard reporting deadlines for the submission of financial (and activity) monitoring information from 3rd party agencies.
| 10.1 | Determine 2014 reporting schedules to senior levels of government | Amanda and Jolanta | bar: February 10
| 10.2 | Create work back schedules establishing City of Hamilton milestones and deadlines we must meet | Lorne and Jolanta | bar: February 17 to March 10
| 10.3 | Schedules should be condensed and incorporated into the timelines of monitoring plans and Contracts | Lorne and Jolanta | bar: February 17 to March 31
| 10.4 | Determine deadlines for the communication of information from 3rd party agencies to the HSD | Lorne and Jolanta | bar: March 24 to March 31
| Evaluation of Outcome | Create Evaluation
Conduct review of how well needs of target population is being served as a result of the changes made through redirecting the CSUMB funding